## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 84 | 66.5 |  |  |  | 21 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0
| 2017-01-17 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Wed | Wed | Wed | Wed | Wed | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-01-11 | 2017-01-13 | 2017-01-15 | 2017-01-18 | 2017-01-20 | 2017-01-22 | 2017-01-25 | 2017-01-27 | 2017-01-29 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | ——Preparation—— | [23 empty] | Assigned
6 | 1 | Play / study original zelda game | OL | LH | 2 |  |  |  | 2 | 2017-01-11: 0; 2017-01-13: 0 | Google search "zelda nes online" and you should figure out how to easily play the game. Otherwise, visit the videogame archive in the basement of the Duderstadt. | Active
7 | 1 | Watch zelda tutorial (canvas) | LH | OL | 2 |  |  |  | 2 | 2017-01-11: 2; 2017-01-13: 0 | There are two Zelda tutorials available for viewing. Read how they're different in the Piazza template repo. | Verify?
8 | 2 | Mess With 494 Quest | LH | OL | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494 Quest was built for you to examine, pilfer, and learn from. | Fixed
9 | 2 | Research and Analysis Paper | OL | LH | 3 | 0 |  |  | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | [25 empty] | Fact of Life
11 | [25 empty] | Can't Repro
12
13
14
15 |  | ——Player Character——
16 | 1 | Grid-based movement | OL | LH | 4 | 0 |  |  | 4 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | Health and damage cooldown (damage-invincibility) | LH |  | 2 | 0 |  |  | 2 | 2 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A nasty side-effect of not implementing a damage cooldown or "vulnerability-period" is that players die exceedingly quickly.
18 | 3 | HUD and Item Selection Capability (item menu). | OL | LH | 3 | 1.5 |  |  | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | Building menus and simple inventory management systems is necessary in many games, and good experience to get. Be thankful you're not making Pokemon, like the F15 class did.
19 | 2 | Collectable Pickup Capability (Hearts, rupees, items) | LH |  | 1 | 1 |  |  | 1 | bar: 2017-01-11 to 2017-02-01
20 | 3 | Bow Weapon Functionality | LH |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
21 | 3 | Boomerang Weapon Functionality | LH |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | The boomerang has many functionalities-- be sure to implement them all!
22 | 3 | Shield - Reflect projectiles. | LH |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
23 | 2 | Bomb Weapon Functionality | LH |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
24
25
26
27
28
29
30
31
32
33
34
35 |  | ——Enemies——
36 | 3 | Stalfos - Skeleton Enemies | OL |  | 2 | 1 |  |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
37 | 1 | Keese - Bat Enemies | OL |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
38 | 1 | Goriya - Boomerang Enemies | OL |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
39 | 3 | Bladetrap - Spike Obstacle Enemies | OL |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
40 | 3 | Gel - Slow Enemies | OL |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
41 | 2 | Wallmaster - Creepy Hand Enemies | OL |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | The wallmaster reset's Link's position in the dungeon, but not the dungeon itself! Don't be lazy and just call Application.LoadLevel()!
42 | 2 | Aquamentus - Dragon Boss | OL |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
43
44
45
46
47
48
49
50 |  | ——Environment——
51 | 1 | Room Transitions |  |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
52 | 1 | Locked Doors |  |  | 1 | 1 |  |  | 1 | bar: 2017-01-11 to 2017-02-01
53 | 2 | Pushable Blocks |  |  | 1 | 1 |  |  | 1 | bar: 2017-01-11 to 2017-02-01
54 | 3 | Old-Man Room (Simple Speech Engine) |  |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Speech and dialogue engines appear in many games, often as the primary driver of plot and character development. Zelda's dialogue system is simple, and provides an opportunity for experience.
55 | 3 | 2D Room (Bow Room) |  |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
56 | 2 | Water tiles (allow projectiles but not physical entities) |  |  | 1 | 1 |  |  | 1 | bar: 2017-01-11 to 2017-02-01
57
58
59
60
61
62 |  | ——Custom Level Stuff Goes Here——
63 | 4 | Custom Level Placeholder |  |  | 30 | 30 |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 |  | Fix Link such that won't get stuck on blocks/walls | LH |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
108 |  | Fix animation for Link's running pattern (State Machine) | LH |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
109 |  | Fix Link grid walking so he doesn't "dance"? (collider) | LH |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
110 |  | Improve detail of sprites (Link and enemies) | OL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
111 |  | Fix damage flashing (not change color of materials) | LH |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
112 |  | Jump back/cooldown time after damage | LH |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
113 |  | Hearts remaining, heart capacity, damage math | OL |  | 2 | 0 |  |  | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
114 |  | Stalfos won't move in proper grid pattern | OL |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
115 |  | Stalfos move too sporadically, need to favor momentum dir | OL |  | 2 | 1 |  |  | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | Active
116 |  | Sword passes through walls?? (trigger vs collider) | LH |  | 1 | 1 |  |  | 1 | [16 empty] | Active | bar: 2017-01-11 to 2017-02-01
117 |  | Little speed/frame number animation details | LH | OL | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | Assigned
118 |  | Doesn't build with proper aspect ratio (256x240) | OL | LH | 1 | 1 |  |  | 1 | [16 empty] | Assigned | bar: 2017-01-11 to 2017-02-01
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 21 | 21 | 19 | 17 | 14 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 84 | 84 | 76 | 68 | 56 | 48 | 40 | 28 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 81 | 81 | 81 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 19 | 16 | 12.5 | 12.5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
216 |  |  | 2 | [5 empty] | 14 | 14 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
217 |  |  | 3 | [5 empty] | 21 | 21 | 21 | 21 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5
218 |  |  | 4 | [5 empty] | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Ori Lindner | OL |  |  |  |  | OL | 33.5 | 30.5 | 26 | 23 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5
223 |  | Lillian Huang | LH |  |  |  |  | LH | 25.5 | 25.5 | 21.5 | 19.5 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236

## Daily Scrum
Producer | Team Members
Approved | Dates |  | Ori Lindner | Lillian Huang
| 2017-01-11 | Wed | Done: Downloaded starter package, started Unity-Zelda project, created and shared repo, made sprites point in intended direction. Next: Figure out how to make Link move on a grid. Help: Make Link not glitch on walls/obstacles. | Done: cloned repo. Next: Read through code, watch tutorials, start analysis report/find another game like Zelda, etc. Help: ---
| 2017-01-13 | Fri | Done: Started Reseach Paper, started implementation of the HUD. Next: Finish research paper, work on HUD, think about enemy implementation. Help: Player controller. | Done: Watched tutorial, read through code, started on Link run animation. Next: Start damage animation/health drops when hitting enemies. Help: Make Link walk on grid; fix "floating" problem when hitting other colliders
| 2017-01-15 | Sun | Done: Finished my portion of Research Paper, finished about 80% of the HUD, implemented updating hearts. Next: Work on developing enemy AI and getting enemy scripts in the game. Help: Script rendering. | Done: Link grid walking, fixed collider issues, damage animation (flash red for a while and have cooldown period where can't get damaged) Next: weapon functionality and animation. Help: --
| 2017-01-18 | Wed | Done: Started and tentatively finished Skeleton.cs AI logic, now moves single sprite in fairly appropriate pattern. Next: Make Stalfos damage Link, get killed by sword, alternate sprites, other enemies. Help: Drop rates of items. How the fuck to use git?! | Done: My half of the Research and Analysis paper, Weapon class, sword functionality when playing Link. Next: Bow, boomerang, shield functionality and animation. Help: git better at git; merge issues, should we start branching, I hate everything
| 2017-01-20 | Fri
| 2017-01-22 | Sun
| 2017-01-25 | Wed
| 2017-01-27 | Fri
| 2017-01-29 | Sun
| 2017-02-01 | Wed
| 2017-02-01 | Wed
| 2017-02-01 | Wed
| 2017-02-01 | Wed
| 2017-02-01 | Wed
| 2017-02-01 | Wed